## Projects
project_name | programme_name | project_type | project_owner | project_description | functions_required | status_override
Plant D MES Concept Study | MES Modernisation | Plant Project | Sarah Chen | Feasibility study for Plant D MES infrastructure upgrade. Draft ”” requirements not yet defined. | Digital Manufacturing, Group IT Enterprise Solutions | Draft
Plant E MES Refresh | MES Modernisation | Plant Project | Marcus Vogel | MES refresh at Plant E. DM MOM/MI&V + GroupIT Data & Integration. Functions Required = [DM]; GroupIT requirements added during Scoping (demonstrates hint-not-binding). | Digital Manufacturing | Scoping
Corporate Data Lake |  | Group Strategy Project | Anya Petrov | Enterprise data lake build. Cross-Function: DM MI&V + GroupIT Data & Integration. No Programme ”” demonstrates Unaligned Projects card. | Digital Manufacturing, Group IT Enterprise Solutions | Submitted
Plant C MES Platform Migration | MES Modernisation | Plant Project | David Lin | Full MES platform migration at Plant C. Headline cross-Function flagship. DM (MOM+MI&V) PartiallyAllocated; GroupIT (Data & Integration) Approved. | Digital Manufacturing, Group IT Enterprise Solutions | Approved
MBM Foundation Library | Digital Twin Rollout | Group Strategy Project | Marcus Vogel | Digital twin foundation library for process simulation. Single-Function DM (MBM). Fully allocated. | Digital Manufacturing | Allocated
Plant B MES Refresh | MES Modernisation | Plant Project | Priya Kumar | MES platform refresh at Plant B. Single-Function DM (MOM). Fully allocated. | Digital Manufacturing | Allocated

## Activities
project_name | activity_name | activity_start_month | activity_end_month | funding_source | funding_notes
Plant D MES Concept Study | Concept & Feasibility | 2026-09 | 2026-10 | Plant/Sector Allocation
Plant D MES Concept Study | Design | 2026-11 | 2027-01 | Investment Scheme
Plant E MES Refresh | Design & Specification | 2026-08 | 2026-09 | Plant/Sector Allocation
Plant E MES Refresh | Build & Integration | 2026-10 | 2026-12 | Plant/Sector Allocation
Corporate Data Lake | Build & Deploy | 2026-07 | 2026-10 | Investment Scheme
Plant C MES Platform Migration | Design & Specification | 2026-06 | 2026-07 | Plant/Sector Allocation | Plant C capital budget
Plant C MES Platform Migration | Build & Integration | 2026-08 | 2026-10 | Plant/Sector Allocation | Plant C capital budget
MBM Foundation Library | Foundation Build | 2026-05 | 2026-08 | Investment Scheme | Digital Twin innovation budget
Plant B MES Refresh | Rollout | 2026-05 | 2026-07 | Plant/Sector Allocation | Plant B budget
direct:Ad-hoc shift pattern review | Review | 2026-07 | 2026-08 | Plant/Sector Allocation
direct:Plant A SCADA migration assist | Migration Support | 2026-07 | 2026-09 | Plant/Sector Allocation
direct:MES Super User support ”” Plant B | Ongoing support | 2026-05 |  | Plant/Sector Allocation | Plant B BAU budget
direct:Historian configuration handover | Handover | 2026-05 | 2026-06 | Plant/Sector Allocation
direct:Plant A OEE enhancement | Implementation | 2026-09 | 2026-10 | Plant/Sector Allocation

## Internal Requirements
project_name | activity_name | skill_function | skill_domain | skill_name | level | hours_per_month | notes
Plant E MES Refresh | Design & Specification | Digital Manufacturing | MOM | MES Platform (core configuration) | Advanced | 60
Plant E MES Refresh | Design & Specification | Digital Manufacturing | MI&V | Data Integration & Pipelines | Advanced | 40
Plant E MES Refresh | Design & Specification | Group IT Enterprise Solutions | Data & Integration | Data Engineering | Advanced | 40
Plant E MES Refresh | Build & Integration | Digital Manufacturing | MOM | MES Platform (core configuration) | Advanced | 80
Plant E MES Refresh | Build & Integration | Digital Manufacturing | MOM | SCADA Integration | Advanced | 40
Plant E MES Refresh | Build & Integration | Group IT Enterprise Solutions | Data & Integration | Data Engineering | Specialist | 60
Plant E MES Refresh | Build & Integration | Group IT Enterprise Solutions | Data & Integration | Integration Architecture | Advanced | 40
Corporate Data Lake | Build & Deploy | Digital Manufacturing | MI&V | Data Integration & Pipelines | Advanced | 40
Corporate Data Lake | Build & Deploy | Group IT Enterprise Solutions | Data & Integration | Data Engineering | Specialist | 80
Corporate Data Lake | Build & Deploy | Group IT Enterprise Solutions | Data & Integration | Integration Architecture | Advanced | 40
Plant C MES Platform Migration | Design & Specification | Digital Manufacturing | MOM | MES Platform (core configuration) | Specialist | 60
Plant C MES Platform Migration | Design & Specification | Digital Manufacturing | MI&V | Data Integration & Pipelines | Advanced | 40
Plant C MES Platform Migration | Design & Specification | Group IT Enterprise Solutions | Data & Integration | Data Engineering | Advanced | 40
Plant C MES Platform Migration | Build & Integration | Digital Manufacturing | MOM | MES Platform (core configuration) | Specialist | 60 | Spawn-time value 60h/mo ”” DM Demand drifted to 80h post-spawn
Plant C MES Platform Migration | Build & Integration | Digital Manufacturing | MOM | Production Workflow Design | Advanced | 40
Plant C MES Platform Migration | Build & Integration | Digital Manufacturing | MI&V | Data Integration & Pipelines | Advanced | 40
Plant C MES Platform Migration | Build & Integration | Group IT Enterprise Solutions | Data & Integration | Data Engineering | Specialist | 60
Plant C MES Platform Migration | Build & Integration | Group IT Enterprise Solutions | Data & Integration | Integration Architecture | Advanced | 40
MBM Foundation Library | Foundation Build | Digital Manufacturing | MBM | Process Simulation | Specialist | 80 | Core simulation framework
MBM Foundation Library | Foundation Build | Digital Manufacturing | MBM | Digital Twin Development | Advanced | 60 | Digital twin integration
Plant B MES Refresh | Rollout | Digital Manufacturing | MOM | MES Platform (core configuration) | Advanced | 60
Plant B MES Refresh | Rollout | Digital Manufacturing | MOM | SCADA Integration | Advanced | 40
direct:Ad-hoc shift pattern review | Review | Digital Manufacturing | MOM | MES Platform (core configuration) | Basic | 20
direct:Plant A SCADA migration assist | Migration Support | Digital Manufacturing | MOM | SCADA Integration | Advanced | 60
direct:MES Super User support ”” Plant B | Ongoing support | Digital Manufacturing | MOM | MES Platform (core configuration) | Basic | 40 | Day-to-day MES support
direct:Historian configuration handover | Handover | Digital Manufacturing | MI&V | Historian Configuration | Advanced | 60
direct:Plant A OEE enhancement | Implementation | Digital Manufacturing | MOM | OEE & Performance Tracking | Advanced | 40
direct:Plant A OEE enhancement | Implementation | Digital Manufacturing | MI&V | Manufacturing Analytics | Advanced | 40

## External Requirements
project_name | activity_name | provider | role | function_tag | hours_per_month | notes
Plant C MES Platform Migration | Build & Integration | OEM | MES Platform Vendor Support | Digital Manufacturing | 40 | OEM provides specialist platform configuration support during build. (Frozen planning record on Project.)
Plant C MES Platform Migration | Build & Integration | Managed Services | SCADA Engineer | Digital Manufacturing | 120 | Managed Services SCADA resource for integration work. (Frozen planning record on Project.)
direct:MES Super User support ”” Plant B | Ongoing support | Other Internal Team | Plant Electrician Support | Digital Manufacturing | 10 | Plant B electricians provide hardware first-line support for MES-connected equipment.
Corporate Data Lake | Build & Deploy | Contractor | Data Engineer | Digital Manufacturing | 80
Corporate Data Lake | Build & Deploy | OEM | Data Platform Vendor | Group IT Enterprise Solutions | 40

## Reference - Programmes
Name | Description
MES Modernisation | Plant-level MES platform upgrades and migrations across the manufacturing estate.
Digital Twin Rollout | Group-wide digital twin capability development, starting with the Line Y pilot.
MI&V Uplift Programme | Manufacturing intelligence and visualisation improvements including data lake integration and OEE standardisation.

## Reference - Skills
Function | Domain | Skill Name
Digital Manufacturing | MOM | MES Platform (core configuration)
Digital Manufacturing | MOM | Production Workflow Design
Digital Manufacturing | MOM | SCADA Integration
Digital Manufacturing | MOM | OEE & Performance Tracking
Digital Manufacturing | MOM | Genealogy & Traceability
Digital Manufacturing | MI&V | Historian Configuration
Digital Manufacturing | MI&V | HMI & Visualisation Design
Digital Manufacturing | MI&V | Reporting & Dashboards
Digital Manufacturing | MI&V | Manufacturing Analytics
Digital Manufacturing | MI&V | Data Integration & Pipelines
Digital Manufacturing | MBM | Process Simulation
Digital Manufacturing | MBM | Digital Twin Development
Digital Manufacturing | MBM | Physics-Based Modelling
Digital Manufacturing | MBM | Process Optimisation
Group IT Enterprise Solutions | Data & Integration | Data Engineering
Group IT Enterprise Solutions | Data & Integration | Integration Architecture
Group IT Enterprise Solutions | Data & Integration | Data Platform Administration
Group IT Enterprise Solutions | Infrastructure & Platforms | Cloud Architecture
Group IT Enterprise Solutions | Infrastructure & Platforms | Network Engineering
Group IT Enterprise Solutions | Infrastructure & Platforms | Platform Engineering
Group IT Enterprise Solutions | Enterprise Applications | ERP Configuration
Group IT Enterprise Solutions | Enterprise Applications | CRM Development
Group IT Enterprise Solutions | Enterprise Applications | Enterprise Application Support

## Reference - Providers
Provider Name
Managed Services
Contractor
OEM
Plant Team
Other Internal Team
Other

## Reference - Project Types
Project Type Name
BAU
NPD Demand
Plant Project
Group Strategy Project

## _lists (hidden)
funding_source | level
Investment Scheme | Basic
Plant/Sector Allocation | Advanced
Mixed | Specialist

## Functions
name | description | active
Digital Manufacturing | Digital manufacturing capability spanning MOM, MI&V and MBM domains across all plants. | true
Group IT Enterprise Solutions | Enterprise IT capability covering infrastructure, applications, and data integration for the group. | true

## Domains
function_name | name | description
Digital Manufacturing | MOM | Manufacturing Operations Management ”” MES, order execution, production tracking, OEE.
Digital Manufacturing | MI&V | Manufacturing Intelligence & Visualisation ”” historians, analytics, dashboards, reporting.
Digital Manufacturing | MBM | Model-Based Manufacturing ”” simulation, digital twins, process modelling.
Group IT Enterprise Solutions | Infrastructure & Platforms | Cloud infrastructure, network engineering, and platform services for the enterprise.
Group IT Enterprise Solutions | Enterprise Applications | ERP, CRM, and enterprise application configuration and development.
Group IT Enterprise Solutions | Data & Integration | Enterprise data engineering, integration architecture, and data platform management.

## Skills
function_name | domain_name | name
Digital Manufacturing | MOM | MES Platform (core configuration)
Digital Manufacturing | MOM | Production Workflow Design
Digital Manufacturing | MOM | SCADA Integration
Digital Manufacturing | MOM | OEE & Performance Tracking
Digital Manufacturing | MOM | Genealogy & Traceability
Digital Manufacturing | MI&V | Historian Configuration
Digital Manufacturing | MI&V | HMI & Visualisation Design
Digital Manufacturing | MI&V | Reporting & Dashboards
Digital Manufacturing | MI&V | Manufacturing Analytics
Digital Manufacturing | MI&V | Data Integration & Pipelines
Digital Manufacturing | MBM | Process Simulation
Digital Manufacturing | MBM | Digital Twin Development
Digital Manufacturing | MBM | Physics-Based Modelling
Digital Manufacturing | MBM | Process Optimisation
Group IT Enterprise Solutions | Data & Integration | Data Engineering
Group IT Enterprise Solutions | Data & Integration | Integration Architecture
Group IT Enterprise Solutions | Data & Integration | Data Platform Administration
Group IT Enterprise Solutions | Infrastructure & Platforms | Cloud Architecture
Group IT Enterprise Solutions | Infrastructure & Platforms | Network Engineering
Group IT Enterprise Solutions | Infrastructure & Platforms | Platform Engineering
Group IT Enterprise Solutions | Enterprise Applications | ERP Configuration
Group IT Enterprise Solutions | Enterprise Applications | CRM Development
Group IT Enterprise Solutions | Enterprise Applications | Enterprise Application Support

## Teams
function_name | name | type | active
Digital Manufacturing | Central Delivery Team | Central | true
Digital Manufacturing | Plant Team A | Plant | true
Digital Manufacturing | Plant Team B | Plant | true
Group IT Enterprise Solutions | Infrastructure Team | Central | true
Group IT Enterprise Solutions | Applications Team | Central | true

## People
name | team_name | contracted_hours | available_from | available_to | active
Alex Morgan | Plant Team A | 152 |  |  | true
Priya Kumar | Plant Team A | 152 |  |  | true
Daniel Okafor | Plant Team A | 152 |  |  | true
Sophie Laurent | Plant Team B | 122 |  |  | true
James Whitfield | Central Delivery Team | 152 |  |  | true
Fatima Al-Rashid | Central Delivery Team | 152 |  |  | true
Ben Carter | Plant Team B | 152 |  |  | true
Naomi Chen | Plant Team B | 152 | 2026-07 |  | true
Marcus Vogel | Central Delivery Team | 152 |  |  | true
Ishani Bhatia | Central Delivery Team | 152 |  |  | true
Tom Ashford | Plant Team A | 152 |  | 2026-10 | true
Olivia Reyes | Plant Team B | 152 |  |  | true
Thomas Richards | Infrastructure Team | 152 |  |  | true
Mei Tanaka | Infrastructure Team | 152 |  |  | true
Luis Fernandez | Applications Team | 152 |  |  | true
Yuki Watanabe | Applications Team | 122 |  |  | true
Anya Petrov | Applications Team | 152 |  |  | true
Henrik Sørensen | Applications Team | 152 | 2026-08 |  | true

## Person Skills
person_name | function_name | domain_name | skill_name | level
Alex Morgan | Digital Manufacturing | MOM | MES Platform (core configuration) | Specialist
Alex Morgan | Digital Manufacturing | MOM | Production Workflow Design | Advanced
Alex Morgan | Digital Manufacturing | MOM | Genealogy & Traceability | Advanced
Priya Kumar | Digital Manufacturing | MOM | MES Platform (core configuration) | Advanced
Priya Kumar | Digital Manufacturing | MOM | SCADA Integration | Specialist
Priya Kumar | Digital Manufacturing | MOM | OEE & Performance Tracking | Advanced
Daniel Okafor | Digital Manufacturing | MOM | Production Workflow Design | Advanced
Daniel Okafor | Digital Manufacturing | MOM | OEE & Performance Tracking | Basic
Daniel Okafor | Digital Manufacturing | MI&V | Reporting & Dashboards | Basic
Sophie Laurent | Digital Manufacturing | MOM | MES Platform (core configuration) | Basic
Sophie Laurent | Digital Manufacturing | MOM | SCADA Integration | Advanced
James Whitfield | Digital Manufacturing | MI&V | Historian Configuration | Specialist
James Whitfield | Digital Manufacturing | MI&V | Data Integration & Pipelines | Advanced
James Whitfield | Digital Manufacturing | MI&V | Manufacturing Analytics | Advanced
Fatima Al-Rashid | Digital Manufacturing | MI&V | Manufacturing Analytics | Specialist
Fatima Al-Rashid | Digital Manufacturing | MI&V | Reporting & Dashboards | Advanced
Fatima Al-Rashid | Digital Manufacturing | MI&V | Data Integration & Pipelines | Advanced
Ben Carter | Digital Manufacturing | MI&V | HMI & Visualisation Design | Advanced
Ben Carter | Digital Manufacturing | MI&V | Reporting & Dashboards | Advanced
Ben Carter | Digital Manufacturing | MI&V | Historian Configuration | Basic
Naomi Chen | Digital Manufacturing | MI&V | HMI & Visualisation Design | Basic
Naomi Chen | Digital Manufacturing | MI&V | Reporting & Dashboards | Basic
Marcus Vogel | Digital Manufacturing | MBM | Process Simulation | Specialist
Marcus Vogel | Digital Manufacturing | MBM | Physics-Based Modelling | Specialist
Marcus Vogel | Digital Manufacturing | MBM | Process Optimisation | Advanced
Ishani Bhatia | Digital Manufacturing | MBM | Digital Twin Development | Advanced
Ishani Bhatia | Digital Manufacturing | MBM | Physics-Based Modelling | Advanced
Ishani Bhatia | Digital Manufacturing | MI&V | Data Integration & Pipelines | Basic
Tom Ashford | Digital Manufacturing | MBM | Process Simulation | Advanced
Tom Ashford | Digital Manufacturing | MBM | Process Optimisation | Advanced
Olivia Reyes | Digital Manufacturing | MBM | Digital Twin Development | Basic
Olivia Reyes | Digital Manufacturing | MBM | Physics-Based Modelling | Basic
Thomas Richards | Group IT Enterprise Solutions | Infrastructure & Platforms | Cloud Architecture | Specialist
Thomas Richards | Group IT Enterprise Solutions | Infrastructure & Platforms | Network Engineering | Advanced
Thomas Richards | Group IT Enterprise Solutions | Infrastructure & Platforms | Platform Engineering | Basic
Mei Tanaka | Group IT Enterprise Solutions | Infrastructure & Platforms | Platform Engineering | Specialist
Mei Tanaka | Group IT Enterprise Solutions | Infrastructure & Platforms | Cloud Architecture | Advanced
Luis Fernandez | Group IT Enterprise Solutions | Enterprise Applications | ERP Configuration | Specialist
Luis Fernandez | Group IT Enterprise Solutions | Enterprise Applications | CRM Development | Advanced
Luis Fernandez | Group IT Enterprise Solutions | Enterprise Applications | Enterprise Application Support | Advanced
Yuki Watanabe | Group IT Enterprise Solutions | Enterprise Applications | CRM Development | Specialist
Yuki Watanabe | Group IT Enterprise Solutions | Enterprise Applications | ERP Configuration | Advanced
Anya Petrov | Group IT Enterprise Solutions | Data & Integration | Data Engineering | Specialist
Anya Petrov | Group IT Enterprise Solutions | Data & Integration | Integration Architecture | Advanced
Anya Petrov | Group IT Enterprise Solutions | Data & Integration | Data Platform Administration | Advanced
Henrik Sørensen | Group IT Enterprise Solutions | Data & Integration | Integration Architecture | Specialist
Henrik Sørensen | Group IT Enterprise Solutions | Data & Integration | Data Engineering | Advanced

## Project Types
name | display_order | colour_token | is_bau | active
BAU | 0 | colour-bau | true | true
NPD Demand | 1 | colour-npd | false | true
Plant Project | 2 | colour-plant-project | false | true
Group Strategy Project | 3 | colour-group-strategy | false | true

## Programmes
name | description | active
MES Modernisation | Plant-level MES platform upgrades and migrations across the manufacturing estate. | true
Digital Twin Rollout | Group-wide digital twin capability development, starting with the Line Y pilot. | true
MI&V Uplift Programme | Manufacturing intelligence and visualisation improvements including data lake integration and OEE standardisation. | true

## Providers
name
Managed Services
Contractor
OEM
Plant Team
Other Internal Team
Other

## Direct Demands
name | function_name | type | owner | description | status
Ad-hoc shift pattern review | Digital Manufacturing | Plant Project | Daniel Okafor | Ad-hoc review of MES shift patterns at Plant A. 1 Activity, 1 MOM Basic requirement. No external. | Draft
Plant A SCADA migration assist | Digital Manufacturing | Plant Project | Priya Kumar | Assist with SCADA migration at Plant A. Submitted ”” Approve is the next-step CTA. | Submitted
MES Super User support ”” Plant B | Digital Manufacturing | BAU | Alex Morgan | Ongoing BAU MES super user support at Plant B. Indefinite Activity; partial allocation in place. Has Other Internal Team external requirement. | PartiallyAllocated
Historian configuration handover | Digital Manufacturing | Plant Project | James Whitfield | Configuration handover for historian upgrade at Plant B. Fully allocated. | Allocated
Plant A OEE enhancement | Digital Manufacturing | Plant Project | Fatima Al-Rashid | OEE metric enhancement at Plant A. Approved, ready for resource planning. | Approved

## Allocations
demand_name | activity_name | skill_name | level | person_name | hours_per_month | notes
Plant C MES Platform Migration | Design & Specification | MES Platform (core configuration) | Specialist | Alex Morgan | 60
Plant C MES Platform Migration | Design & Specification | Data Integration & Pipelines | Advanced | James Whitfield | 40
Plant C MES Platform Migration | Build & Integration | MES Platform (core configuration) | Specialist | Alex Morgan | 60 | Partial ”” 20 hrs/mo unplanned
Plant C MES Platform Migration | Build & Integration | Data Integration & Pipelines | Advanced | James Whitfield | 40
MBM Foundation Library | Foundation Build | Process Simulation | Specialist | Marcus Vogel | 80
MBM Foundation Library | Foundation Build | Digital Twin Development | Advanced | Ishani Bhatia | 60
Plant B MES Refresh | Rollout | MES Platform (core configuration) | Advanced | Priya Kumar | 60
Plant B MES Refresh | Rollout | SCADA Integration | Advanced | Sophie Laurent | 40
MES Super User support ”” Plant B | Ongoing support | MES Platform (core configuration) | Basic | Daniel Okafor | 20
Historian configuration handover | Handover | Historian Configuration | Advanced | James Whitfield | 60